## Tasks
Task List
buisness modeling |  |  | Hours Expected
understand the buisness environment
|  | Review Current System | 10
|  | determine people affected by new system | 2
create the system vision
|  | define system objectives | 10
|  | list system capabilities | 5
|  | identify primary buisness benefits | 5
create buisness models
|  | Document Buisness Processes | 4
|  | Document Information Repositories | 1
requirements
gather detailed information
|  | buisness rules | 5
|  | current process | 5
define functional requirements
|  | analyze current paper system | 5
|  | interview users | 0.5
define nonfunctional requirements
prioritize requirements
|  | determine most important requirements | 5
|  | analyze the feasibility of additional features vs cost and importance | 5
develop user interface dialogs
|  | develop story boards | 5
|  | query users about story boards | 0.5
evaluate requirements with users
|  | Present requirements to users | 0.5
|  | Present prioritized requirments | 0.5
Design
Design The Support Services architecture and deployment environment
|  | Review existing architecture of the environment | 3
|  | determine modifications that must be made to existing system to suppot new system | 5
Design the software
|  | develop design class diagram | 3
|  | Tailor to fit any existing architecture or designed architecture | 3
Design use case realizations
|  | Document class interaction in detail | 10
|  | Illistrate use case realizations | 10
Design The database
|  | determine needed tables | 5
|  | create rough database schema | 5
design the system and user interfaces
|  | anaylaze and compare to current system for similarities | 5
|  | detailed story boards | 15
Design the system security and controls
Implementation
Build Software Components
|  | Build Windows Components | 300
|  | Build web Componenets | 80
Acquire software components
|  | Acquire any required software components | 1
|  | Acquure any required licenses | 1
Integrate Software Components
|  | Integrate Software Packages | 10
|  | Integrate components | 10
Testing
Define and Conduct unit testing
|  | Create test plan | 30
|  | create test cases | 30
|  | debug code | 10
define and conduct integration testing
|  | Establish contacts with vendors of existing systems | 5
|  | Develop testing guidelines based integration reqirements | 5
define and conduct usability testing
|  | Develop usability test | 10
|  | conduct the test | 10
Define and conduct user acceptance testing
|  | Design test cases | 15
|  | Execute test cases | 15
Deployment
Acquire hadware and system software
|  | Develop Request for Proposal | 10
|  | Evaluate Results | 5
|  | Install and configure new hardware and system software | 10
Package and install components
|  | install components | 8
|  | implement any parts of existing system that are being kept | 10
train users
|  | determine users skills and proficiencys | 0.5
|  | identify levels of training different users need | 0.5
|  | Train Users | 1
convert and initialize data
|  | obtain data from old source | 5
|  | Convert old data to be usable with new system | 10
|  | Construct new Database | 20
Project Management
Evaluate the project's scpoe and risks
|  | Ensure all reqs listed with the risk of each | 2
|  | Involve users to insure all reqs known | 0.5
Confirm the Project's Feasibility
|  | Risk analysis | 3
|  | review analysis | 2
Develop the project and iteration schedules
|  | Determine itteration length | 1
|  | determine tasks that will fit in iteration | 5
Monitor and control the projects iterations
|  | Document late iterations in detail | 1
|  | Asses changes needed | 2
Configurations and change Management
Develop change control procedures
|  | develop version management standard | 5
|  | implement change and error reporting system | 5
manage models and software components
|  | Create doc for changes | 5
|  | Create communication guidelines | 5
Environment
Delect and configure development tools
|  | determine best tools | 2
|  | get needed licenses and software | 2
Tailor the up development process
|  | Determine best UP variation for desiered environment | 2
Provide technical support services
|  | Develop Documentation | 30
|  | Train service staff | 40
|  | Total Hours | 857.5

## Benefits
Tangable Benefits Saving Breakdown
Year 1
Benefit/Cost Savings | Amount | Comments
Increased Efficiency | 28000 | 2 More Services Per day @ $50
Increased Sales | 46800 | 3 more sales per Week @300
Less Paper | 780 | 15 Dollar Savings Per Week
Total | 75580
Year 2
Benefit/Cost Savings | Amount | Comments
Increased Efficiency | 42000 | 3 more Services Per Day @ $50
Increased Sales | 78000 | 5 More Sales Per Week @300
Less Paper | 1040 | 20 Dollar Savings Per Week
Total | 121040
Year 3
Benefit/ Cost Savings | Amount | Comments
Increased Efficiency | 56000 | 4 more Services Per Day @ $50
Increased Sales | 93600 | 6 More Sales Per Week @300
Less Paper | 1040 | 20 Dollar Savings Per Week
Total | 150640
Year 4
Benefit/Cost Savings | Amount | Comments
Increased Efficiency | 70000 | 5 more Services Per Day @ $50
Increased Sales | 109200 | 7 More Sales Per Week @300
Less Paper | 1300 | 25 Dollar Savings Per Week
Total | 180500
Year 5
Benefit/Cost Savings | Amount | Comments
Increased Efficiency | 84000 | 6 more Services Per Day @ $50
Increased Sales | 109200 | 7 More Sales Per Week @300
Less Paper | 1300 | 25 Dollar Savings Per Week
Total | 194500

## Economic Feasability
Economic Feasability
Cost Benefit Analysis | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Value Of Benefits |  | 75580 | 121040 | 150640 | 180500 | 194500
Discount Factor(10%) | 1 | 0.9091 | 0.8264 | 0.7513 | 0.683 | 0.6209
Present Value Of Benefits |  | 68709.778 | 100027.456 | 113175.832 | 123281.5 | 120765.05 | 525959.616
Development Costs | -128625 | [5 empty] | -128625
Ongoing Costs |  | 12500 | -12500 | -12500 | -12500 | -12500
Discount Factor(10%) | 1 | 0.9091 | 0.8264 | 0.7513 | 0.683 | 0.6209
Present Value Of Costs |  | 11363.75 | -10330 | -9391.25 | -8537.5 | -7761.25 | -24656.25
PV of Net of benefits and costs | -128625 | 80073.528 | 89697.456 | 103784.582 | 114744 | 113003.8
Cumulative NPV | -128625 | -48551.472 | 41145.984 | 144930.566 | 259674.566 | 372678.366
Pay Back Period | 2 years 289 days
5 Year Retun on Investment | 443.1%

## Costs
Costs
Labor Total Cost
Labor Rate (Per Hour) | Total Hours | Total Cost
150 | 857.5 | 128625
Hardware Cost Totals
Amount | Item | Cost
2 | Computers Running Windows 7 Pro | 2000
1 | Router | 100
1 | Firewall | 400
Total
4 |  | 2500
Annual Support Cost
1 | 12 Months Mantenance | 5000
1 | 12 Months System Support | 7500
Total
2 |  | 12500
Total Initial Costs
Amount | Item | Cost
857.5 | Labor Hours | 128625
4 | Hardware Costs Total | 2500
2 | Support Costs | 12500
Totals
863.5 |  | 143625

## Work Log
Work Log
Time Spent Workin On task
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Review Current System | 5 | 2 | 3
determine people affected by new system | 1 | 1
define system objectives
list system capabilities | 5 | 5
identify primary buisness benefits | 2 | 1 | 2
Document Buisness Processes
Document Information Repositories
buisness rules | 4
current process | 1
analyze current paper system
interview users
determine most important requirements | 5
analyze the feasibility of additional features vs cost and importance | 5
develop story boards
query users about story boards |  | 5
Present requirements to users
Present prioritized requirments
Review existing architecture of the environment
determine modifications that must be made to existing system to suppot new system
develop design class diagram
Tailor to fit any existing architecture or designed architecture
Document class interaction in detail
Illistrate use case realizations
determine needed tables
create rough database schema
anaylaze and compare to current system for similarities
detailed story boards
Build Windows Components
Build web Componenets
Acquire any required software components
Acquure any required licenses |  |  | 3
Integrate Software Packages |  |  | 2
Integrate components
Create test plan
create test cases
debug code
Establish contacts with vendors of existing systems
Develop testing guidelines based integration reqirements
Develop usability test
conduct the test
Design test cases
Execute test cases
Develop Request for Proposal
Evaluate Results
Install and configure new hardware and system software
install components
implement any parts of existing system that are being kept
determine users skills and proficiencys
identify levels of training different users need
Train Users
obtain data from old source
Convert old data to be usable with new system
Construct new Database
Ensure all reqs listed with the risk of each
Involve users to insure all reqs known
Risk analysis
review analysis
Determine itteration length
determine tasks that will fit in iteration
Document late iterations in detail
Asses changes needed
develop version management standard
implement change and error reporting system
Create doc for changes
Create communication guidelines
determine best tools
get needed licenses and software
Determine best UP variation for desiered environment
Develop Documentation
Train service staff

## Event List and Resulting Use Ca
Event | Use Cases
Manager deletes Employee | Delete Employee
Manager Updates Employee | update Employee
Manager Creates New Employee | Create Employee
Clock In menu Item Clicked | Employee Clocks In
Clock out menu item Clicked | Employee Clocks out
Customer Name Entered | Customer Looked Up
Employee Clicks Create New Customer Button | Create New Customer
Customer Brings Bike In for Service | Enter Service Ticket
Employee Creates new service | Create New Service item
Employee Edits Service | Update Service item
Employee Deletes service Item | Delete Service Item
Application Start | Load service Queue
Employee Creates Product item | Create Product
Employee Deletes Product Item | Delete Product Item
Employee Updates Product Item | Update Prodcut Item
Employee Creates New Bike Item | Cerate New Bike Item
Employee Deletes New Bike Item | Delete New Bike Item
Employees Checks Out Customer | Check Out Cutstomer
Complete Bike Service | Update Bike Service Status
Employe Wants to change Password | Change Password
Manager Wants to see Employee Service Report | Employee Service Report
Manager Wants to see Service Reprt | Show Service Report

## attributelist
Credentail Class
EmpID | employee ID | int
Password | Employee Entered Password | string
NewPassword | Employee New Password | string
confirmPass | Employee Entered Confirm New Password | string
passCompare | Password Pulled from database to compare to | string
loginPass | if password was good | boolean
Employee Class
employeeID | employee ID | int
employeeFirstName | Employee First Name | string
employeeLastName | Employee Last Name | string
employeeAddress1 | Employee Address Line 1 | string
employeeAddress2 | Employee Address Line 2 | string
employeeCity | Employee City | string
employeeState | Employee State | string | 2 characters
employeeZip | Emmployee Zip Code | int | 5 characters
employeePhone | Employee Phone | string | 7 characters
employeeAreaCode | Employee Area Code | string | 3 characters
emplpyeePayRate | Employee Pay Rate | double
Reciept Class
aCustomer | A customer Object | customer object
aEmployee | A Employee Object | employee object
items | a arraylist of item objects | arraylist
subtotal | Subtotal or purchase | double
total | total cost of purchase after tax | double
paymentType | type of payment(cash or creditcard) | string
creditCardNumber | credit card number | string
paymentAmount | the amount of the payment | double
Service Class
serviceID | ID of a service | int
serviceName | name of a service | string
serviceType | type of service | string
serviceDescrip | description of service | string | 255characters max
serviceCost | The cost of the service | double
BikeService Class
bServiceID | id of service ticket | int
aCustomer | a customer object | customer object
aCustomerBike | a customer bike object | customer bike object
bServiceDescription | desciption of service | string | 255 characters max
bServices | list of service objects customer would like | arraylist of services
bServiceEnteredBy | name of employee whoo entered service | string
bServiceEmpNmae | name of service tech | string
bServiceStatus | status of the service | string
bCostofServices | total cost of services | double
CustomerBike Class
cBikeID | id of Customer Bike | int
cBikeBrand | brand of customer Bike | string
cBikeModel | Model of customer bike | string
cBikeSerialNumber | Serial Number of Customer Bike | string
New Bike Class
nBikeID | Id of A new Bike | int
nBikeBrand | Brand of new bike | string
nBikeModel | model of new bike | string
nBikeSerialNumber | sieral number of new bike | string
nBikeType | type of new bike | string
nBikeCost | cost of new bike | double
ProductClass
prodID | id of product | int
prodSKU | sku of product | string
prodName | name of product | string
prodType | type of prodcut | string
prodCost | cost of product | double
Customer Class
customerID | Customer Id | int
customerFirstName | Customer First Name | string
customerLastName | Customer Last Name | string
customerAddress1 | Customer Address Line 1 | string
customerAddress2 | Customer Address line 2 | string
customerCity | Customer City | string
customerState | customer state | string | 2characters
customerZip | customer zip | int | 5charcters
customerPhone | customer phone | string | 7characters
customerAreaCode | customer area code | string | 3 charaters