## Tasks
Task List
buisness modeling |  |  | Hours Expected
understand the buisness environment
|  | Review Current System | 10
|  | determine people affected by new system | 2
create the system vision
|  | define system objectives | 10
|  | list system capabilities | 5
|  | identify primary buisness benefits | 5
create buisness models
|  | Document Buisness Processes | 4
|  | Document Information Repositories | 1
requirements
gather detailed information
|  | buisness rules | 5
|  | current process | 5
define functional requirements
|  | analyze current paper system | 5
|  | interview users | 0.5
define nonfunctional requirements
prioritize requirements
|  | determine most important requirements | 5
|  | analyze the feasibility of additional features vs cost and importance | 5
develop user interface dialogs
|  | develop story boards | 5
|  | query users about story boards | 0.5
evaluate requirements with users
|  | Present requirements to users | 0.5
|  | Present prioritized requirments | 0.5
Design
Design The Support Services architecture and deployment environment
|  | Review existing architecture of the environment | 3
|  | determine modifications that must be made to existing system to suppot new system | 5
Design the software
|  | develop design class diagram | 3
|  | Tailor to fit any existing architecture or designed architecture | 3
Design use case realizations
|  | Document class interaction in detail | 10
|  | Illistrate use case realizations | 10
Design The database
|  | determine needed tables | 5
|  | create rough database schema | 5
design the system and user interfaces
|  | anaylaze and compare to current system for similarities | 5
|  | detailed story boards | 15
Design the system security and controls
Implementation
Build Software Components
|  | Build Windows Components | 300
|  | Build web Componenets | 80
Acquire software components
|  | Acquire any required software components | 1
|  | Acquure any required licenses | 1
Integrate Software Components
|  | Integrate Software Packages | 10
|  | Integrate components | 10
Testing
Define and Conduct unit testing
|  | Create test plan | 30
|  | create test cases | 30
|  | debug code | 10
define and conduct integration testing
|  | Establish contacts with vendors of existing systems | 5
|  | Develop testing guidelines based integration reqirements | 5
define and conduct usability testing
|  | Develop usability test | 10
|  | conduct the test | 10
Define and conduct user acceptance testing
|  | Design test cases | 15
|  | Execute test cases | 15
Deployment
Acquire hadware and system software
|  | Develop Request for Proposal | 10
|  | Evaluate Results | 5
|  | Install and configure new hardware and system software | 10
Package and install components
|  | install components | 8
|  | implement any parts of existing system that are being kept | 10
train users
|  | determine users skills and proficiencys | 0.5
|  | identify levels of training different users need | 0.5
|  | Train Users | 1
convert and initialize data
|  | obtain data from old source | 5
|  | Convert old data to be usable with new system | 10
|  | Construct new Database | 20
Project Management
Evaluate the project's scpoe and risks
|  | Ensure all reqs listed with the risk of each | 2
|  | Involve users to insure all reqs known | 0.5
Confirm the Project's Feasibility
|  | Risk analysis | 3
|  | review analysis | 2
Develop the project and iteration schedules
|  | Determine itteration length | 1
|  | determine tasks that will fit in iteration | 5
Monitor and control the projects iterations
|  | Document late iterations in detail | 1
|  | Asses changes needed | 2
Configurations and change Management
Develop change control procedures
|  | develop version management standard | 5
|  | implement change and error reporting system | 5
manage models and software components
|  | Create doc for changes | 5
|  | Create communication guidelines | 5
Environment
Delect and configure development tools
|  | determine best tools | 2
|  | get needed licenses and software | 2
Tailor the up development process
|  | Determine best UP variation for desiered environment | 2
Provide technical support services
|  | Develop Documentation | 30
|  | Train service staff | 40
|  | Total Hours | 857.5

## Benefits
Tangable Benefits Saving Breakdown
Year 1
Benefit/Cost Savings | Amount | Comments
Increased Efficiency | 28000 | 2 More Services Per day @ $50
Increased Sales | 46800 | 3 more sales per Week @300
Less Paper | 780 | 15 Dollar Savings Per Week
Total | 75580
Year 2
Benefit/Cost Savings | Amount | Comments
Increased Efficiency | 42000 | 3 more Services Per Day @ $50
Increased Sales | 78000 | 5 More Sales Per Week @300
Less Paper | 1040 | 20 Dollar Savings Per Week
Total | 121040
Year 3
Benefit/ Cost Savings | Amount | Comments
Increased Efficiency | 56000 | 4 more Services Per Day @ $50
Increased Sales | 93600 | 6 More Sales Per Week @300
Less Paper | 1040 | 20 Dollar Savings Per Week
Total | 150640
Year 4
Benefit/Cost Savings | Amount | Comments
Increased Efficiency | 70000 | 5 more Services Per Day @ $50
Increased Sales | 109200 | 7 More Sales Per Week @300
Less Paper | 1300 | 25 Dollar Savings Per Week
Total | 180500
Year 5
Benefit/Cost Savings | Amount | Comments
Increased Efficiency | 84000 | 6 more Services Per Day @ $50
Increased Sales | 109200 | 7 More Sales Per Week @300
Less Paper | 1300 | 25 Dollar Savings Per Week
Total | 194500

## Economic Feasability
Economic Feasability
Cost Benefit Analysis | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Value Of Benefits |  | 75580 | 121040 | 150640 | 180500 | 194500
Discount Factor(10%) | 1 | 0.9091 | 0.8264 | 0.7513 | 0.683 | 0.6209
Present Value Of Benefits |  | 68709.778 | 100027.456 | 113175.832 | 123281.5 | 120765.05 | 525959.616
Development Costs | -128625 | [5 empty] | -128625
Ongoing Costs |  | 12500 | -12500 | -12500 | -12500 | -12500
Discount Factor(10%) | 1 | 0.9091 | 0.8264 | 0.7513 | 0.683 | 0.6209
Present Value Of Costs |  | 11363.75 | -10330 | -9391.25 | -8537.5 | -7761.25 | -24656.25
PV of Net of benefits and costs | -128625 | 80073.528 | 89697.456 | 103784.582 | 114744 | 113003.8
Cumulative NPV | -128625 | -48551.472 | 41145.984 | 144930.566 | 259674.566 | 372678.366
Pay Back Period | 2 years 289 days
5 Year Retun on Investment | 443.1%

## Costs
Costs
Labor Total Cost
Labor Rate (Per Hour) | Total Hours | Total Cost
150 | 857.5 | 128625
Hardware Cost Totals
Amount | Item | Cost
2 | Computers Running Windows 7 Pro | 2000
1 | Router | 100
1 | Firewall | 400
Total
4 |  | 2500
Annual Support Cost
1 | 12 Months Maintenance | 5000
1 | 12 Months System Support | 7500
Total
2 |  | 12500
Total Initial Costs
Amount | Item | Cost
857.5 | Labor Hours | 128625
4 | Hardware Costs Total | 2500
2 | Support Costs | 12500
Totals
863.5 |  | 143625

## Work Log
Work Log
Time Spent Workin On task
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | week7 | week8 | week9
Review Current System | Time Spent Workin On task Week 1: 5; Time Spent Workin On task Week 2: 2; Time Spent Workin On task Week 3: 3
determine people affected by new system | bar: Time Spent Workin On task Week 1 to Time Spent Workin On task Week 2
define system objectives
list system capabilities | Time Spent Workin On task Week 1: 5; Time Spent Workin On task Week 2: 5
identify primary buisness benefits | Time Spent Workin On task Week 1: 2; Time Spent Workin On task Week 2: 1; Time Spent Workin On task Week 3: 2
Document Buisness Processes
Document Information Repositories
buisness rules | Time Spent Workin On task Week 1: 4
current process | bar: Time Spent Workin On task Week 1
analyze current paper system
interview users
determine most important requirements | Time Spent Workin On task Week 1: 5
analyze the feasibility of additional features vs cost and importance | Time Spent Workin On task Week 1: 5
develop story boards
query users about story boards | Time Spent Workin On task Week 2: 5
Present requirements to users | Time Spent Workin On task Week 4: 0.5
Present prioritized requirments | Time Spent Workin On task Week 4: 0.5
Review existing architecture of the environment | Time Spent Workin On task Week 4: 2
determine modifications that must be made to existing system to suppot new system | Time Spent Workin On task Week 4: 2
develop design class diagram | Time Spent Workin On task Week 4: 2
Tailor to fit any existing architecture or designed architecture | Time Spent Workin On task Week 4: 2
Document class interaction in detail | Time Spent Workin On task Week 4: 2
Illistrate use case realizations | Time Spent Workin On task Week 4: 2
determine needed tables | Time Spent Workin On task Week 4: 2
create rough database schema | Time Spent Workin On task Week 4: 2
anaylaze and compare to current system for similarities | Time Spent Workin On task Week 4: 2
detailed story boards | Time Spent Workin On task Week 4: 2
Build Windows Components | Time Spent Workin On task Week 5: 120
Build web Componenets | Time Spent Workin On task Week 5: 0
Acquire any required software components | Time Spent Workin On task Week 5: 0
Acquure any required licenses | Time Spent Workin On task Week 5: 0
Integrate Software Packages | Time Spent Workin On task Week 5: 0
Integrate components | Time Spent Workin On task Week 6: 0
Create test plan | Time Spent Workin On task Week 6: 5
create test cases | Time Spent Workin On task Week 6: 5
debug code | Time Spent Workin On task Week 6: 30
Establish contacts with vendors of existing systems | Time Spent Workin On task Week 6: 0
Develop testing guidelines based integration reqirements | Time Spent Workin On task Week 6: 2
Develop usability test | bar: Time Spent Workin On task Week 6
conduct the test | Time Spent Workin On task Week 6: 10
Design test cases | bar: Time Spent Workin On task Week 6
Execute test cases | bar: Time Spent Workin On task Week 6
Develop Request for Proposal | bar: Time Spent Workin On task Week 6
Evaluate Results | Time Spent Workin On task week7: 0
Install and configure new hardware and system software | Time Spent Workin On task week7: 0
install components | Time Spent Workin On task week7: 0
implement any parts of existing system that are being kept | bar: Time Spent Workin On task week7
determine users skills and proficiencys | bar: Time Spent Workin On task week7
identify levels of training different users need | bar: Time Spent Workin On task week7
Train Users | bar: Time Spent Workin On task week7
obtain data from old source | bar: Time Spent Workin On task week7
Convert old data to be usable with new system | bar: Time Spent Workin On task week7
Construct new Database | bar: Time Spent Workin On task week7
Ensure all reqs listed with the risk of each | bar: Time Spent Workin On task week8
Involve users to insure all reqs known | bar: Time Spent Workin On task week8
Risk analysis | bar: Time Spent Workin On task week8
review analysis | bar: Time Spent Workin On task week8
Determine itteration length | bar: Time Spent Workin On task week8
determine tasks that will fit in iteration | bar: Time Spent Workin On task week8
Document late iterations in detail | bar: Time Spent Workin On task week8
Asses changes needed | bar: Time Spent Workin On task week8
develop version management standard | bar: Time Spent Workin On task week8
implement change and error reporting system | bar: Time Spent Workin On task week8
Create doc for changes | bar: Time Spent Workin On task week8
Create communication guidelines | Time Spent Workin On task week9: 2
determine best tools | Time Spent Workin On task week9: 2
get needed licenses and software | Time Spent Workin On task week9: 2
Determine best UP variation for desiered environment | Time Spent Workin On task week9: 2
Develop Documentation | Time Spent Workin On task week9: 2
Train service staff | Time Spent Workin On task week9: 0

## Event List and Resulting Use Ca
Event | Use Cases
Employee Gets Fired or Quits | Delete Employee
Employee Information Changes | update Employee
New Employee Hired By Store | Create Employee
Employee Shows Up to Work | Employee Clocks In
Employee Leaving Work | Employee Clocks out
Customer Wants To make Purchase or Drip Bike Off | Customer Looked Up
New Customer wants to make purchase or drop bike off | Create New Customer
Customer Brings Bike In for Service | Enter Service Ticket
Employee Creates new service | Create New Service item
Information About Service Changes | Update Service item
Service No Longer Offerd | Delete Service Item
Application Start | Load service Queue
Shop Recieves a new Item that isn't in system | Create Product
Employee Updates Product Item | Update Prodcut Item
New Bike Not in system already | Cerate New Bike Item
Employees Checks Out Customer | Check Out Cutstomer
Complete Bike Service | Update Bike Service Status
Employe Wants to change Password | Change Password
Manager Wants Employee Service Report | Employee Service Report
Manager Wants Item Sales Report | Item Sales Report

## attributelist
Credentail Class
EmpID | employee ID | int
Password | Employee Entered Password | string
NewPassword | Employee New Password | string
confirmPass | Employee Entered Confirm New Password | string
passCompare | Password Pulled from database to compare to | string
loginPass | if password was good | boolean
Employee Class
employeeID | employee ID | int
employeeFirstName | Employee First Name | string
employeeLastName | Employee Last Name | string
employeeAddress1 | Employee Address Line 1 | string
employeeAddress2 | Employee Address Line 2 | string
employeeCity | Employee City | string
employeeState | Employee State | string | 2 characters
employeeZip | Emmployee Zip Code | int | 5 characters
employeePhone | Employee Phone | string | 7 characters
employeeAreaCode | Employee Area Code | string | 3 characters
emplpyeePayRate | Employee Pay Rate | double
Reciept Class
aCustomer | A customer Object | customer object
aEmployee | A Employee Object | employee object
items | a arraylist of item objects | arraylist
subtotal | Subtotal or purchase | double
total | total cost of purchase after tax | double
paymentType | type of payment(cash or creditcard) | string
creditCardNumber | credit card number | string
paymentAmount | the amount of the payment | double
Service Class
serviceID | ID of a service | int
serviceName | name of a service | string
serviceType | type of service | string
serviceDescrip | description of service | string | 255characters max
serviceCost | The cost of the service | double
BikeService Class
bServiceID | id of service ticket | int
aCustomer | a customer object | customer object
aCustomerBike | a customer bike object | customer bike object
bServiceDescription | desciption of service | string | 255 characters max
bServices | list of service objects customer would like | arraylist of services
bServiceEnteredBy | name of employee whoo entered service | string
bServiceEmpNmae | name of service tech | string
bServiceStatus | status of the service | string
bCostofServices | total cost of services | double
CustomerBike Class
cBikeID | id of Customer Bike | int
cBikeBrand | brand of customer Bike | string
cBikeModel | Model of customer bike | string
cBikeSerialNumber | Serial Number of Customer Bike | string
New Bike Class
nBikeID | Id of A new Bike | int
nBikeBrand | Brand of new bike | string
nBikeModel | model of new bike | string
nBikeSerialNumber | sieral number of new bike | string
nBikeType | type of new bike | string
nBikeCost | cost of new bike | double
ProductClass
prodID | id of product | int
prodSKU | sku of product | string
prodName | name of product | string
prodType | type of prodcut | string
prodCost | cost of product | double
Customer Class
customerID | Customer Id | int
customerFirstName | Customer First Name | string
customerLastName | Customer Last Name | string
customerAddress1 | Customer Address Line 1 | string
customerAddress2 | Customer Address line 2 | string
customerCity | Customer City | string
customerState | customer state | string | 2characters
customerZip | customer zip | int | 5charcters
customerPhone | customer phone | string | 7characters
customerAreaCode | customer area code | string | 3 charaters